## Feature List
|  | Planned Points | Overall Progress | Current Points
|  | 66 | 25.76% | 17
Category | Feature | Points | % Complete | Responsible | Pivot Table Report | % Complete
Hosting | Running on cosc304 server | 2 | 100% |  | Daniella | 16.67%
Main/Home Page | Search for a product by name | 1 | 100% |  | Ability to enter a review on a product | 0%
Main/Home Page | Browse products by category | 1 | 100% |  | Display product review on product detail | 0%
Main/Home Page | List products (by search/browse) | 1 | 100% |  | Restrict to one review per user on item purchased | 50%
Main/Home Page | List products with image | 2 | 0% | William | Igat | 10%
Main/Home Page | Page header with menu | 1 | 100% |  | Create user account page | 0%
Main/Home Page | Page header shows current logged in user | 1 | 0% | Igat | Create user account with data validation | 0%
Shopping Cart | Add to shopping cart | 1 | 100% |  | Login/logout | 50%
Shopping Cart | View shopping cart | 1 | 100% |  | Page header shows current logged in user | 0%
Shopping Cart | Update item quantity in shopping cart | 2 | 100% |  | Secured by login | 0%
Shopping Cart | Remove item from shopping cart | 1 | 100% |  | Jon | 10.71%
Shopping Cart | Improved formatting/UI (e.g. in header bar) | 1 | 100% |  | Calculate taxes and shipping cost | 0%
Checkout | Checkout with customer id | 1 | 100% |  | Change order status/ship order | 0%
Checkout | Checkout with payment/shipment info | 2 | 0% | Jon | Checkout with data validation | 0%
Checkout | Checkout with data validation | 3 | 0% | Jon | Checkout with payment/shipment info | 0%
Checkout | Calculate taxes and shipping cost | 2 | 0% | Jon | Database restore with SQL script | 75%
Product Detail Page | Product detail page and item description | 3 | 75% | William | Implement some validation using triggers | 0%
Product Detail Page | Product detail has an image | 1 | 100% |  | Report with a graph | 0%
Product Detail Page | Product detail has an image from database | 4 | 0% | William | William | 25%
User Accounts and Login | Create user account page | 3 | 0% | Igat | Add new product | 25%
User Accounts and Login | Create user account with data validation | 3 | 0% | Igat | List products with image | 0%
User Accounts and Login | Login/logout | 2 | 50% | Igat | Product detail has an image from database | 0%
User Accounts and Login | Page listing all orders for user | 1 | 100% |  | Product detail page and item description | 75%
Product Reviews | Ability to enter a review on a product | 2 | 0% | Daniella | Update/delete product | 50%
Product Reviews | Display product review on product detail | 1 | 0% | Daniella | Upload a photo to database for product | 0%
Product Reviews | Restrict to one review per user on item purchased | 2 | 50% | Daniella | Up for Grabs
Administrator Portal | Secured by login | 3 | 0% | Igat | Use AJAX for some pages
Administrator Portal | List all customers | 1 | 100%
Administrator Portal | List report showing total sales/orders | 1 | 100%
Administrator Portal | Report with a graph | 3 | 0% | Jon
Administrator Portal | Add new product | 2 | 25% | William
Administrator Portal | Update/delete product | 2 | 50% | William
Administrator Portal | Change order status/ship order | 1 | 0% | Jon
Administrator Portal | Upload a photo to database for product | 4 | 0% | William
Administrator Portal | Database restore with SQL script | 2 | 75% | Jon
Database System/General | Implement some validation using triggers | 2 | 0% | Jon
Database System/General | Use AJAX for some pages | 4 |  | Up for Grabs
Database System/General | Bonus – User interface and navigation/usability